## Sheet1
PROJECT INFORMATION REGISTER
Construction (Design & Management) Regulations 2007
PROJECT: K&CTMO - Fire door replacement programme |  |  |  |  | CLIENT: Kensington & Chelsea TMO
LEAD DESIGNER: |  |  |  |  | STRUCTURAL ENGINEER:
PRINCIPAL CONTRACTOR (if appointed): |  |  |  |  | CDM CO-ORDINATOR: Baily Garner Health & Safety Ltd
PREPARED BY: Alan Thomas |  |  |  |  | DATE: 4th January 2011
| Information Required by |  |  | Additional Information Required by |  |  |  | Information Provided - task complete
PROJECT: K&CTMO - Fire door replacement programme |  |  |  |  | CLIENT: Kensington & Chelsea TMO
Ref | Nature of Information | Client | Lead Designer | CDM-C | Struct Eng. | Mech Eng. | Elec Eng. | PC | Comments
|  | KCTMO |  | BG H&S
1 | KEY STAGE 1 (up to production of Pre-Construction Information Pack)
1.1 | Establish Project directory. Project Notification | see attached property list | [6 empty] | Notification form received. Please provide full list address' for this project.
1.2 | Designer/ contractor competence assessment needed | We are doing via a Framework via London Housing Consortium, would we require this info, if so will get info from LHC | [6 empty] | Client to advise on appointment
1.3 | Issue of F10 Initial Notification to HSE and Client | [7 empty] | To be actioned
1.4 | Health and Safety file(s) for previous works | Not available | [6 empty] | Any existing H&S Files for previous works to these properties
1.5 | Drawings of the existing structure | [7 empty] | In relation to works areas in addition to specification
1.6 | Records of mains services on site | [7 empty] | In relation to works areas
1.7 | Details of any ground investigations/surveys | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable in relation to works
1.8 | Details of any condition surveys carried out on existing boundaries | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable in relation to works
1.9 | Details of any asbestos surveys carried out for existing buildings (management plans) | [7 empty] | Is there an existing register or are surveys to be carried out please confirm
1.1 | Details of specific site conditions or risk register | See attached our Virex List | [6 empty] | Any specific site conditions anti social behaviour etc
1.11 | Details of any existing potentially hazardous substances | [7 empty] | Please confirm in specification and designers risk appraisal
1.12 | Details of any potentially hazardous substances in the proposed design | [7 empty] | Please confirm in specification and designers risk appraisal
1.13 | Designer's risk appraisal / evaluation process required | [7 empty] | Designer to forward to CDM-C
1.14 | Issue/agree of Pre-Construction Health & Safety Information Pack | [7 empty] | Await information from para's 1.1 to 2.6
PROJECT: K&CTMO - Fire door replacement programme |  |  |  |  | CLIENT: Kensington & Chelsea TMO
Ref | Nature of Information | Client | Lead Designer | CDM-C | Struct Eng. | Mech Eng. | Elec Eng. | PC | Comments
|  | KCTMO |  | BG H&S
2 | KEY STAGE 2 (up to commencement of construction works on site)
2.1 | Residual hazards/ information from foundation design | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable in relation to works
2.2 | Residual hazards/ information from structural design | [7 empty] | Any works required to lintels etc applicable to the works
2.3 | Residual hazards/ information from door design | [7 empty] | Are locking devises being considered when operation to be carried out by elderly, infirm or disabled residents
2.4 | Residual hazards/ information from services design | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable in relation to works
2.5 | Residual hazards/ information from roof design | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable in relation to works
2.6 | Drawings of the proposed works e.g. layouts, elevations and sections | [7 empty] | Please forward any available drawings to CDM-C
2.7 | Review design and maintenance appraisal | [7 empty] | On going throughout design process
2.8 | Restrictions on access to the site and the works | [7 empty] | Details in Construction Phase Health & Safety Plan
2.9 | Review and agree PC's Construction Phase Health & Safety Plan. Agree dates for Key Stage 3 | [7 empty] | Await P.C CPH&SP
2.1 | Issue of F10 'Declaration' to HSE | [7 empty] | Await P.C CPH&SP
2.11 | Confirmation to Client of satisfactory CPHSP | [7 empty] | Await P.C CPH&SP
2.12 | Client notification to commence construction | [7 empty] | Await approval of CPH&SP
PROJECT: K&CTMO - Fire door replacement programme |  |  |  |  | CLIENT: Kensington & Chelsea TMO
Ref | Nature of Information | Client | Lead Designer | CDM-C | Struct Eng. | Mech Eng. | Elec Eng. | PC | Comments
|  | KCTMO |  | BG H&S
3 | KEY STAGE 3 (up to practical completion)
3.1 | Review of outstanding design information | [7 empty] | On going throughout works
3.2 | Attend site project progress meetings | [7 empty] | At key stages in the programme
3.3 | Attend site to discuss H&S File contents with PC | [7 empty] | Roughly 4-6 weeks before completion is due
3.4 | Ensure CPHSP maintained by PC | [7 empty] | On going throughout works
3.5 | Provide all information for Health & Safety File | [7 empty] | On going throughout works
3.6 | Ensure HSF is prepared
3.7 | Issue of HSF to Client