## Front Sheet (CON E11)
Front Sheet
Project: Enhancements & Improvements to Grenfell Tower, Kensington | [7 empty] | Date: | 31.03.14
Form : E11
Tender Nr : RML027
| BQ Figure | [6 empty] | 7325450.43
| Preliminaries |  |  |  |  | 12.6011 | % | 923086
Discount
| Subcontractors |  |  |  |  | -154206.915
| Materials |  |  |  |  | -733.5652 |  | -154940.4802
Adjustments (Std +20%)
(£14.17) | Groundworker |  |  |  |  | 0
(£41.75) | Bricklayer |  |  |  |  | 0
(£16.86) | Carpenter |  |  |  |  | 0 |  | 0
| Fixed Price |  | Start : | 2014-06-01
0 | GW | 2014-07-01
| GW | 2015-01-01
| GW | 2015-07-01
14128.41 | BL | 2014-07-01
| BL | 2015-01-01
| BL | 2015-07-01
121536.67 | CJ | 2014-07-01
| CJ | 2015-01-01
| CJ | 2015-07-01
293426.07 | Materials |  | 293426.07 | x7%x50%x | 62 | 12244.8956
52
6683809.34 | Subcontractors |  |  |  |  | 0
0 | Muck Away (£ /load) |  |  | tax? |  | 0
0 | Other Plant |  |  |  |  | 0
212550 | Prov |  |  |  |  | 0 |  | 12244.8956 |  | 0.1402% | p.a.
7325450.49 | [9 empty] | 0.2804% | inflation
| Fees | [6 empty] | 272997
8378837.8454
| Performance |  | 10% on provisional sums |  |  | -0.25432 | % | -21255
8357582.8454
| Less Provisional Sums | [6 empty] | -212550
8145032.8454
| Margin |  |  |  |  | 10.9479 | % | 891711.5857
| Add Provisional Sums | [6 empty] | 212550
9249294.4311
EM Sig:
BID £
MD Sig:

## Tender Analysis (CON E13)
Tender Analysis Sheet
Project: Enhancements & Improvements to Grenfell Tower, Kensington |  |  |  |  | Date: | 31.03.14
Total Area : | 1 | m2 |  | Average Area : | 1 | m2
Nr Units : | 1 | Nr
|  |  | Unit | M2 | Total
SUBSTRUCTURES |  |  | 19261.37 | 19261.37 |  | 19261.37
WORKS TO EXISTING STRUCTURE |  |  | 130490.72 | 130490.72 |  | 130490.72
CORE ALTERATIONS |  |  | 63406.32 | 63406.32 |  | 63406.32
CLADDING & WINDOWS |  |  | 3228479.22 | 3228479.22 |  | 3228479.22
SUPERSTRUCTURE |  |  | 135903.67 | 135903.67 |  | 135903.67
7 NR NEW UNITS |  |  | 158740.98 | 158740.98 |  | 158740.98
WORKS TO EXISTING FLATS |  |  | 391048 | 391048 |  | 391048
& COMMON AREAS
NURSERY & PLAY AREA |  |  | 97218.96 | 97218.96 |  | 97218.96
EMB OFFICES |  |  | 55835.03 | 55835.03 |  | 55835.03
BOXING CLUB |  |  | 90266.94 | 90266.94 |  | 90266.94
WORKS TO UNDERCROFT |  |  | 9725 | 9725 |  | 9725
M&E |  |  | 2274621.71 | 2274621.71 |  | 2274621.71
EXISTING GARAGES |  |  | 36074.37 | 36074.37 |  | 36074.37
EXTERNAL WORKS |  |  | 361408.45 | 361408.45 |  | 361408.45
DRAINAGE |  |  | 31367.83 | 31367.83 |  | 31367.83
SEVICES |  |  | 5025.93 | 5025.93 |  | 5025.93
FACILITATING WORKS |  |  | 24025.93 | 24025.93 |  | 24025.93
PROVISIONAL SUMS |  |  | 212550 | 212550 |  | 212550
|  |  | 7325450.43 | 7325450.43 |  | 7325450.43
PRELIMS |  |  | 923086 | 923086 |  | 923086
DISCOUNT |  |  | -154940.4802 | -154940.4802 |  | -154940.4802
FIXED PRICE |  |  | 12244.8956 | 12244.8956 |  | 12244.8956
FEES |  |  | 272997 | 272997 |  | 272997
|  |  | 8378837.8454 | 8378837.8454 |  | 8378837.8454
PERFORMANCE |  |  | -21255 | -21255 |  | -21255
MARGIN |  |  | 891711.5857 | 891711.5857 |  | 891711.5857
|  |  | 9249294.4311 | 9249294.4311 |  | 9249294.4311 | 9249294.4311
|  |  | 9249294.4311 | 9249294.4311

## Fees (CON E12)
Rydon Construction Limited |  |  |  | Fees |  |  |  |  | 2026-07-29 15:31
Project:
[9 empty] | Approximate Value : | 10000000
[8 empty] | Contract Period : | 62 | weeks
Consultants
Architect : | [6 empty] | Studio E |  |  | 180626
Structural Engineering : | [6 empty] | Curtins |  |  | 36999
Civil Engineering : | [9 empty] | 0
Mechanical and Electrical Engineer : | [6 empty] | Mechanical Subcontractor |  |  | 0
Planning Consultant | [9 empty] | 0
Acoustic Consultant | [9 empty] | 0
Contamination : Merebrook
Fire Consultant | [9 empty] | 7500
0
Landscape Architect : | [9 empty] | 0
Adoption
Section 104 (Drainage) |  |  | @ | 5 | % |  |  |  | 0
Section 38 (External Works) |  |  | @ | 8 | % |  |  |  | 0
|  | 0 | @ | 2 | % | x | 114 | / 52 | 0 | 0
Legal Agreements |  |  | @ | 400 | [5 empty] | 0
Building Control
Plans | [8 empty] | 0
|  |  | @ | 0.89 |  |  |  |  | 0
Inspection | [8 empty] | 0
|  | 0 | @ | 2.67 |  |  |  |  | 0 | 7500
Insurance
NHBC Buildmark Choice | [9 empty] | 0
Contractors All-Risks Insurance - for schemes over £25M (£5M for timber frame) | [8 empty] | FALSE | N/A
Clause 21.2.1 Insurance for schemes rated High Risk | [9 empty] | N/A
Planning Permission
|  | 0 | m2 @ | 335 | (per 75 m2) |  |  |  | 0
|  | 0 | m2 @ | 100 | (per 75 m2) |  |  |  | 0 | 0
| or | [7 empty] | (max. £250,000)
|  | 0 | Nr @ | 335 | (per unit) |  |  |  | 0
|  | 0 | Nr @ | 100 | (per unit) |  |  |  | 0 | 0
Planning Conditions Discharge Fee |  | 15 | Nr @ | 85 | (per request) |  |  |  |  | 1275
Miscellaneous
Soil Investigation | [9 empty] | 2000
Site Survey | [9 empty] | 2000
Traffic Survey | [9 empty] | 0
Drainage cctv survey | [9 empty] | 1500
Party Wall Surveyors |  |  | @ | 2000 | [5 empty] | 0
Sound Survey |  |  | floor survey |  | @ |  | 95 |  | 0
|  |  | wall survey |  | @ |  | 85 |  | 0
|  |  | insulation report | 1 | @ |  | 360 |  | 360 | 360
SAP & EPC | [6 empty] | Bailey Garner |  |  | 5516
SBEM Calcs for L2A | [9 empty] | 0
Code for Sustainable Homes | [6 empty] | Bailey Garner |  |  | 2476
BREEAM | [6 empty] | Bailey Garner |  |  | 9645
Ecology | [9 empty] | 0
Air Pressure Testing (dwellings) |  |  |  | 120 | @ |  | 125 |  |  | 15000
Considerate Contractor | [9 empty] | 600
TRADA FrameCheck (for timber frame only) |  |  |  |  | @ |  | 1980 | per visit |  | 0
Postal numbering |  |  |  |  | @ |  | 20 |  |  | 0
O&M Manuals |  |  |  |  | @ |  | 25
Total Design & Build Fees | [9 empty] | 272997
Landscaping allowance:
No Requirement | Nil
Up to 1 Acre | 430
Up to 2 Acres | 748
Up to 3 Acres | 1059
Up to 4 Acres | 1325
Up to 5 Acres | 1591
Up to 6 Acres | 1857
Up to 7 Acres | 2123

## Provisional Sums
Provisional Sums
1 | Signage | Sum | 20000
2 | Replacement of duct panels to Riser | Sum | 20000
3 | Asbestos removal | Sum | 100000
4 | Replacement of bathroom central extract fans | Sum | 8000
5 | Replacement of rubbish chute central extract fans | Sum | 3000
6 | Attenuation of boiler room supply fan | Sum | 2000
7 | Attenuation of smoke system supply fan | Sum | 2000
8 | Provision of ventilation grille to gas risers for each flat | Sum | 40000
9 | Add for percentage on the Provisional Sums total of £195,000.00
| @ ……9…… % | Sum | 17550
212550
195000
| Allow 12.5% in CSA |  | 24375

## VE
Grenfell Tower
Value Engineering Options
|  | Tender Value | Saving Offered | Margin Generated
Windows & Curtain Walling
| Windows - simplified arrangement | TBC | TBC
| Cladding - Aluminium in lieu of zinc | -419267 | -293067 | 126200
| Crown designed to roof | -52004 | -35004 | 17000
| Louvre panel located over tilt & turn windows | -80074 | -60074 | 20000
M&E
| Under floor heating to gf lobby | -2574 | -2574
| Lobby pipework | N/A | N/A
| Alternative Flue Manufacturer | -28650 | -20650 | 8000
| Carbon Steel distribution pipework in lieu of S/S | -28870 | -20870 | 8000
Internals
| Pre-finished board in lieu of birchwood surround | -176608.3333 | -116608 | 60000.3333
Landscaping
| Omit works to Play Area | -78356 | -91532 | -13176 | Value identified in CSA
| Omit Soft Landscaping | -27825 | -20825 | 7000
| Omit Hard Landscaping | -111776 | -85776 | 26000
| Reduce spec on remaining block paviours | -17760 | -14760 | 3000
General
| Eco funding grant | -100000 | -100000 | 0
|  | -1123764.3333 | -861740 | 262024.3333

## Preliminaries (CON E09) GAH
Rydon Maintenance - Preliminaries
Project: Enhancements & Improvements to Grenfell Tower, Kensington |  |  |  | Date: | 2013-12-02 |  | Costed To: | [6 empty] | Date: | 2026-07-29 15:31 |  | Budget No 1
[6 empty] | NOTES | COST (From C.V. wks complete) | [7 empty] | Loss/Gain | NOTES | Previous Budget | Difference
|  |  |  | 62 | weeks |  |  | To Date | Liability | Transfer | Sub Total | To Come |  | Total | £'s |  |  |  | Time Related | Fixed | Increases | CSA Split
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
SUPERVISION
Project Manager (Simon O Connor) |  | 62 | wks | 1078 | 66836 | Supervision | [14 empty] | 2802.8 |  | Supervision
Site Manager (Ian West) |  | 62 | wks | 803 | 49786 | Supervision | [14 empty] | 2087.8 |  | Supervision
Site Manager (James Young) |  | 50 | wks | 913 | 45650 | Supervision | [14 empty] | 2373.8 |  | Supervision
Site Manager (Mick Sullivan) |  | 54 | wks | 862 | 46548 | Supervision | [14 empty] | 2241.2 |  | Supervision
Trainee Site Agent - TBC |  | 50 | wks | 779 | 38950 | Supervision | [14 empty] | 2025.4 |  | Supervision
RLO (Chtistina Stephanou) |  | 62 | wks | 755 | 46810 | Supervision | [14 empty] | 1963 |  | Supervision
Design Co-ordinator (Simon Lawrence) |  | 15 | wks | 1500 | 22500 | Supervision | [16 empty] | Supervision
Planning |  |  | wks |  | 0 | Supervision | [16 empty] | Supervision
Increases | 2014-10-01 | 5% |  |  | 13494 | Supervision
0
| Operatives / wk | 5.7258 | [8 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 330574 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
LABOURERS |  |  |  |  | 0
0
Labourer 1 | Welfare & RLO assistant | 42 | wks | 400 | 16800 | Attendances | [14 empty] | 1040 |  | Supervision
Labourer 2 | (Gateman/traffic marshall) | 62 | wks | 400 | 24800 | Attendances | [14 empty] | 1040 |  | Supervision | Supervision | 388706
Labourer 3 (Cleaner) |  | 37 | wks | 400 | 14800 | Attendances | [14 empty] | 1040 |  | Plant | Accommodation | 53145
|  |  | wks | 400 | 0 | [18 empty] | Services | 106986
|  |  | wks | 400 | 0 | [18 empty] | Plant | 117355
[5 empty] | 0 | [18 empty] | Temporary | 9500
Handyman |  | 20 | wks | 540 | 10800 | Attendances
[5 empty] | 0 | [19 empty] | 675692
Increases | 2014-10-01 | 5% |  | 3120 | 156 | Attendances | [18 empty] | 675692
[5 empty] | 0 | [19 empty] | 0
| Operatives / wk | 2.5968 | [8 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 67356 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
APPRENTICE |  |  |  |  | 0
0
General allowance (Job Specific) |  | 20 | item | 3000 | 60000 | Via Livetrain course.e
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 60000 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
TIME / ADMIN | [10 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
IT Connection (varies approx 0.1% contract sum) |  | 1 | item | 6000 | 6000 | Site Establishment | [16 empty] | Services
Connect Phones |  | 1 | item | 300 | 300 | Site Establishment | [16 empty] | Services
Fax & photocopier |  | 1 | item | 1000 | 1000 | Site Establishment | [16 empty] | Services
Electricity |  | 62 | wks | 60 | 3720 | Temporary Services | [16 empty] | Services
Telephone |  | 62 | wks | 75 | 4650 | Temporary Services | [16 empty] | Services
Building Water (0.15% of contract sum) |  | 1 | item | 9000 | 9000 | Temporary Services | [16 empty] | Services
Office Expenses & Entertainment |  | 62 | wks | 100 | 6200 | Sundries | [16 empty] | Services
O & M Manual administration |  | 1 | item | 5000 | 5000 | Sundries
Travel/ Motor |  |  |  |  | 0
| Project Manager (Simon O Connor) | 62 | Wks | 100 | 6200 | Supervision | [16 empty] | Supervision
| Site Manager (Ian West) |  | Wks | 100 | 0 | Supervision |  |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
| Site Manager (James Young) | 50 | Wks | 100 | 5000 | Supervision |  |  |  |  | 0 |  | 0 | 0 | 5000 |  |  | 5000 |  |  |  |  | Supervision
| Site Manager (Mick Sullivan) | 54 | Wks | 100 | 5400 | Supervision |  |  |  |  | 0 |  | 0 | 0 | 5400 |  |  | 5400 |  |  |  |  | Supervision
| Trainee Site Agent - TBC | 50 | Wks | 100 | 5000 | Supervision |  |  |  |  | 0 |  | 0 | 0 | 5000 |  |  | 5000 |  |  |  |  | Supervision
| RLO | 62 | Wks | 100 | 6200 | Supervision |  |  |  |  | 0 |  | 0 | 0 | 6200 |  |  | 6200 |  |  |  |  | Supervision
| Design Co-ordinator (Simon Lawrence) | 15 |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Surveyor |  | Wks | 100 | 0 | Supervision |  |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
| Other Visiting |  | Wks |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Subsistence |  | Wks |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
0
| Allowance / wk | 1026.9355
Allowance / m2
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 63670 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 21600 |  |  | 21600
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
PLANT | [10 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
0
Access Equipment(101) |  |  | item |  | 0
Accommodation(102) |  |  | item |  | 0
| Office - Main Site | 62 | wks | 35 | 2170 | Accommodation | [16 empty] | Accommodation
| Office - RLO | 62 | wks | 35 | 2170 | Accommodation | [16 empty] | Accommodation
| Meeting Room | 62 | wks | 60 | 3720 | Accommodation | [16 empty] | Accommodation
| Roll along | 0 | wks |  | 0 | Accommodation
| Canteen/Drying Room | 62 | wks | 40 | 2480 | Accommodation | [16 empty] | Accommodation
| Drying Room | 62 | wks | 35 | 2170 | Accommodation | [16 empty] | Accommodation
| Respite Accommodation | 1 | item | 5000 | 5000 | Accommodation | [16 empty] | Accommodation
| Staircase | 62 | wks | 15 | 930 | Accommodation | [16 empty] | Accommodation
| Gate Hut | 1 | item | 2000 | 2000 | Accommodation | [16 empty] | Accommodation
| Toilet | 62 | wks | 42.5 | 2635 | Accommodation | [16 empty] | Accommodation
| Effluent Tank | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
| Steps | 124 | wks | 2.5 | 310 | Accommodation | [16 empty] | Accommodation
| Emptying Service | 31 | wks | 120 | 3720 | Accommodation | [16 empty] | Accommodation
| Tool Vault/Security Box | 0 | wks |  | 0 | Accommodation
| Container 1 | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
| Container 2 | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
| Container 3 | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
| Container 4 | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
| Container 5 | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
| Container 6 | 62 | wks | 10 | 620 | Accommodation | [16 empty] | Accommodation
Rates (if over 12 months) |  | 0 | wks |  | 0
Heaters/Dehumidifiers |  | 0 | wks | 50 | 0
Theodolites/Levels(104) (50% of time) |  | 0 | wks | 25 | 0
Mixers(105) |  | 0 | wks |  | 0
Road Sweepers(106) |  |  | No | 60 | 0
Generators(112) |  |  | wks | 400 | 0
Transport & Erect(116) (Minimum £2000) |  | 1 | item | 3500 | 3500 | Site Establishment | [16 empty] | Accommodation
Purchases(120) (Minimum £2000) |  | 1 | item | 3000 | 3000 | Plant | [16 empty] | Supervision
Stolen Items(122) |  | 0 | item | 0 | 0
Small Tools/Plant hire Sundries(123) |  | 62 | wks | 50 | 3100 | Plant | [16 empty] | Services
Fire Point |  | 4 | no | 500 | 2000 | Plant
0
| Allowance / wk | 697.5 | [8 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Allowance / m2 | [9 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 43245 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Forklift / Mechanical Plant | [10 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Scissor Lift |  |  | wks | 250 | 0 | Plant
Driver |  | 0 | wks | 460 | 0
Fuel |  | 0 | wks | 100 | 0
Repairs |  |  | item |  | 0
High Level Access |  | 1 | item | 5000 | 5000 | Plant | [16 empty] | Plant
Other Mech Plant |  |  |  |  | 0
| Scissors Lift |  |  |  | 0
0
| Allowance / wk | 80.6452
Allowance / m2
0
[5 empty] | 5000 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Crane(118) |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
0
Base |  | 0 | item | 10000 | 0
Fixing Angles |  | 0 | item | 4500 | 0
Transport/Erect/Dismantle |  | 0 | item | 11800 | 0
Signs |  | 0 | item | 2200 | 0
Floodlights |  | 0 | item | 1600 | 0
Crane & Driver |  | 0 | wks | 2300 | 0
Driver Bonus |  | 0 | wks | 100 | 0
Power/Generator/Fuel |  | 0 | wks | 400 | 0
Skips, chains & radios (buy) |  | 0 | item | 3000 | 0
Banksman |  | 0 | wks | 460 | 0
Over sailing Licences |  | 0 | item | 1000 | 0
0
Mobile Crane |  | 12 | No | 500 | 6000 | Plant | [16 empty] | Plant
0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Allowance / wk | 96.7742 | [8 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Allowance / m2 | [9 empty] | 0 |  | 0 | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 6000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
Hoists (Goods & Passenger) |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Transport, Erect & Dismantle |  | 1 | item | 6485 | 6485 | [5 empty] | 0 |  | 0 | 0 | 6485 |  |  | 6485 |  |  |  |  | Plant
Additonal Dismantle Visit |  |  | nr | 350 | 0
Electrical Connection |  | 1 | item | 1500 | 1500 | [17 empty] | Plant
Call bell system |  |  | item | 3435 | 0
Training (upto 8 persons) |  | 5 | item | 450 | 2250 | [17 empty] | Plant
Hoistway Protection Panels |  | 5 | nr | 140 | 700 | [17 empty] | Plant
Landing Infill Plates |  | 5 | nr | 115 | 575 | [17 empty] | Plant
Base Plates |  | 44 | wks | 30 | 1320 | [17 empty] | Plant
Base Ramp |  | 1 | item | 475 | 475 | [17 empty] | Plant
Hire |  | 44 | wks | 125 | 5500 | [5 empty] | 0 |  | 0 | 0 | 5500 |  |  | 5500 |  |  |  |  | Plant
Power |  | 44 | wks | 200 | 8800 | [5 empty] | 0 |  | 0 | 0 | 8800 |  |  | 8800 |  |  |  |  | Plant
Generator/Tank 250KVA |  |  | wks | 210 | 0 | assumed connect on site |  |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
Transport For Generator/Tank |  |  | nr | 90 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Lightning Protection |  | 1 | item | 750 | 750 | [17 empty] | Plant
[5 empty] | 28355 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 20785 | 0 |  | 20785
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Compound / Site Set Up |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
0
Connect WC's |  | 1 | item | 300 | 300 | Site Establishment | [16 empty] | Services
Erect and Strike Huts |  | 1 | item | incl. | incl.
Temporary Road |  | 0 | item | 0 | 0
Hut Paths |  |  | item | 500 | 0 | Site Establishment
Tree Protection |  | 0 | m | 35 | 0 | [17 empty] | Temporary
Site Board |  | 1 | item | 1250 | 1250 | Site Establishment | [16 empty] | Temporary
Sign Board |  | 1 | item | 1250 | 1250 | Site Establishment | [16 empty] | Temporary
Heras Fencing |  | 100 | m | 15 | 1500 | Site Establishment | [16 empty] | Temporary
Hoarding 2.4m |  | 100 | m | 55 | 5500 | Site Establishment | [16 empty] | Temporary
Hoarding 3.0m |  | 0 | m | 80 | 0
Gates |  |  | item | 1000 | 0 | Site Establishment
Electric Connection & Leads |  | 1 | item | 5000 | 5000 | Site Establishment | [16 empty] | Services
Furniture | (inc respite) | 1 | item | 3000 | 3000 | Site Establishment | [16 empty] | Accommodation
Security Gate System |  | 1 | item | 15000 | 15000 | Site Establishment | [16 empty] | Accommodation
Electric Connection & Leads |  | 1 | item | 10000 | 10000 | Site Establishment |  |  |  |  | 0 |  | 0 | 0 | 10000 |  |  | 10000 |  |  |  |  | Services
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 42800 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 10000 | 0 |  | 10000
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Skips(100) |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
0
Skips (100) | 1.5 | 1 | item | 30000 | 30000 | Recycling/ Removal of Rubbish | [16 empty] | Services
0
0
0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 30000 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
MAST CLIMBERS |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Position 1 - 14 |  |  |  | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Transport | 8 | nr | 900 | 7200 | [5 empty] | 0 |  | 0 | 0 | 7200 |  |  | 7200 |  |  |  |  | Plant
| Erect | 8 | nr | 800 | 6400 | [5 empty] | 0 |  | 0 | 0 | 6400 |  |  | 6400 |  |  |  |  | Plant
| Strip | 8 | nr | 800 | 6400 | [17 empty] | Plant
| Hire 8 x 45weeks | 360 | wks | 120 | 43200 | [5 empty] | 0 |  | 0 | 0 | 43200 |  |  | 43200 |  |  |  |  | Plant
|  |  | wks | 120 | 0
|  |  | wks | 120 | 0
| Debris Netting | 8 | nr | 125 | 1000 | [5 empty] | 0 |  | 0 | 0 | 1000 |  |  | 1000
| Chemical Anchors | 8 | nr | 240 | 1920 | [5 empty] | 0 |  | 0 | 0 | 1920 |  |  | 1920
| Power £50/week per cradle | 45 | wks | 400 | 18000 | [5 empty] | 0 |  | 0 | 0 | 18000 |  |  | 18000
| Training | 5 | item | 450 | 2250
| Lightning Protection | 1 | item | 750 | 750
| Test | 8 | nr | 250 | 2000
SCAFFOLD |  |  |  |  | 0
As per scaffodl schedule
North Elevation |  | 1 | item | 7920 | 7920 | [5 empty] | 0 |  | 0 | 0 | 7920 |  |  | 7920
East Elevation |  | 1 | item | 16830 | 16830
Haki Staircase |  | 1 | item | 1500 | 1500
Hoist Tower |  | 1 | item | 675 | 675
South Elevation |  | 1 | item | 5610 | 5610
South Elevation |  | 1 | item | 3300 | 3300
Haki Staircase |  | 1 | item | 900 | 900
Back Propping |  | 1 | item | 3968 | 3968
Public Access Staircase |  | 1 | item | 14601 | 14601
Bricklayers Acccess & Loading bays |  | 1 | item | 2460 | 2460
Debris Netting |  | 1 | item | 160 | 160
Weekly Scaffod Inspections |  | 50 | nr | 150 | 7500
Design Input |  | 1 | item | 2000 | 2000 | [5 empty] | 0 |  | 0 | 0 | 2000 |  |  | 2000
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Allowance / wk | 2609.0667 | [8 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| Allowance / m2 | 156544 | [8 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 156544 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 87640 | 0 |  | 87640
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
MAINTENANCE |  |  |  |  | 0
0
Units - 12 months |  | 120 | No | 50 | 6000 | Protection | [16 empty] | Services
Units - 24 months (private) |  | 0 | No | 250 | 0
Schools/Health |  |  | m2 | 4 | 0
Communal |  |  |  |  | 0
Roads |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Maintenance - Allowance |  | 1 | item | 35000 | 35000 | Protection |  |  |  |  | 0 |  | 0 | 0 | 35000 |  |  | 35000
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 41000 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 35000 | 0 |  | 35000
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
CLEANER |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Final Clean - Dwellings |  |  | No | 100 | 0 | Protection |  |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
Cleaning - Communal Areas |  |  |  |  | 2000 | Protection |  |  |  |  | 0 |  | 0 | 0 | 2000 |  |  | 2000 |  |  |  |  | Services
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 2000 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 2000 | 0 |  | 2000
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
MATERIALS |  |  |  |  | 0
0
Protection |  | 120 | nr | 80 | 9600 | Protection | [16 empty] | Services
Replacements (1% of material value excl. GW) |  | 1 | item | 3916 | 3916 | Protection | [16 empty] | Services
Prelim Materials (4% of ditto) |  | 62 | wks | 100 | 6200 | Protection | [16 empty] | Services
Residuals | (-1% of ditto) | 1 | item | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Piling Mat (if not in BQ) |  | 1 | item | 0 | 0
Show Units |  | 0 | nr |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 19716 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
SECURITY |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Guard 1 |  |  | wks | 825 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Guard 2 |  |  | wks | 825 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Cameras |  |  | item |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Holidays & Christmas period |  |  | item |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
BOND |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
10% Bond to PC |  | 1 | item | 26826 | 26826 | Sundries |  |  |  |  | 0 |  | 0 | 0 | 26826 |  |  | 26826
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 26826 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 26826 | 0 |  | 26826
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
MOCK UP WORKS |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
Curtain Wall mock up |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
balcony door mock up |  |  | item | 1750 | 0 | Sundries |  |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
scaffold structure, steps, handrail |  |  | item | 500 | 0 | Sundries |  |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[11 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
TOTAL PRELIM |  |  |  |  | 923086 | 923086
PRELIMINARIES
[5 empty] | 324470 |  | Final Clean | [11 empty] | Supervision
[5 empty] | 67356 |  | Health & Safety | [11 empty] | Attendances
[5 empty] | 30000 |  | Sundries | [11 empty] | Recycling/ Removal of Rubbish
[5 empty] | 31645 |  | Fees | [11 empty] | Accommodation
[5 empty] | 53600 |  | Printing, Stationery & Document Production | [11 empty] | Site Establishment
[5 empty] | 17370 |  | Employment & Skills Plan | [11 empty] | Temporary Services
[5 empty] | 19100 |  | 0 | [11 empty] | Plant
[5 empty] | 62716 |  | 0 | [11 empty] | Protection
[5 empty] | 38026 |  | 0 | [11 empty] | Sundries
644283
|  |  |  | Mast Climbers | 156544
|  |  |  | Hoist | 28355
|  |  |  | Milestone | 33904
863086

## Bond Calculation (CON E08)
| BOND PRICING |  | Updated 04.07.12
A. | Standard 10% Bonds / on ABI or other Standard Wording
| Bond Sum | Release Event (PC/MGD) | Contract Period in Weeks (to PC) Minimum 52 weeks | Maintenance Period in Weeks (only if releases on MGD) | Estimated cost
| 1000000 | PC | 62 |  | 14903.8462
|  |  |  | Total cost | 14903.8462
B. | On Demand / Funding / Bonds Greater than 10%
B.1 | Bond Sum | Release Event (PC/MGD) | Contract Period in Weeks (to PC) Minimum 52 weeks | Maintenance Period in Weeks (only if releases on MGD) | Estimated cost
0
B.2 | Bank Guarantee / Uplift in Premium |  |  |  | CONTACT LEGAL DEPT
0
|  |  |  | Total cost | 0
C. | Aspire bonds
C.1 | Bond Sum | Release Event (PC/MGD) | Contract Period in Weeks (to PC) Minimum 52 weeks | Maintenance Period in Weeks (only if releases on MGD) | Estimated cost
0
|  |  |  | Total cost | 0

## SC Comparison (CON E07)
Subcontractor Comparison
SURVEYORS PERFORMANCE ASSESSMENT
Project: Enhancements & Improvements to Grenfell Tower, Kensington | [7 empty] | 31.03.14
[9 empty] | Value Less | Cost Less | Gain | % Gain
Trade / Subcontractor | Quote |  | Firm | Disc | Used | Disc | FP Add | Notes | Discount | Discount
|  |  |  | % | £ | £ | £
AOV'S - inc in mechanical | [8 empty] | 0 | 0 | 0 | 0%
Fire Design Solutions |  | 55560 |  | Nett |  |  |  | can suggest significant VE savings | 0 | 0 | 0 | 0%
JS Wright |  | 78988
[9 empty] | 0 | 0 | 0 | 0%
Blind Installation | [8 empty] | 0 | 0 | 0 | 0%
Kaydee Blinds | USED | 2620.29 |  | Nett | 2620.29 | 0 |  |  | 2620.29 | 2620.29 | 0 | 0%
Levolux |  | 4820 |  | 2.5 |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Block Paviors | [8 empty] | 0 | 0 | 0 | 0%
HPS | USED | 104563.64 |  | Nett | 104563.64 | 0 |  |  | 104563.64 | 104563.64 | 0 | 0%
GPB |  | 111344.5 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
A T KNOTT |  | 127140.5 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Hamilton |  | 128418 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Ceramic Tiling | [8 empty] | 0 | 0 | 0 | 0%
The Tiling Co | USED | 13980 |  | Nett | 13980 | 0 |  |  | 13980 | 13980 | 0 | 0%
Gordon Lomond |  | 14238 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Composite Floors - inc in GW | [8 empty] | 0 | 0 | 0 | 0%
SWUK |  | 10608.88 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Prodeck-Fixing Ltd |  | 9072 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Hamilton |  | 14203.12 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
HPS |  | 10188 |  | Nett |  |  |  |  | #REF! | #REF! | #REF! | 0%
[9 empty] | 0 | 0 | 0 | 0%
Curtain Walling | [8 empty] | 0 | 0 | 0 | 0%
Harley Curtain Wall | USED | 3218360 |  | 3 | 3218360 | 96550.8 |  |  | 3121809.2 | 3121809.2 | 0 | 0% | 3218360
Structal |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Red Architecural |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Prater |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Structura |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Hansen Facades |  | 3402038 |  | 2,5 |  |  |  |  | 0 | 0 | 0 | 0% | 3316987.05
Advanced Glass Facades Ltd |  | 2993792.75 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0% | 2993792.75
LSC Facades Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Glassolutions Saint-Gobain |  | 3192113.38 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0% | 3192113.38
SN Murdoch Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
3d Alumimium Plas Ltd |  | 3057322 |  | 2,5 |  |  |  |  | 0 | 0 | 0 | 0% | 2980888.95
Fill Metallbau |  | 3253597 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0% | 3253597
[9 empty] | 0 | 0 | 0 | 0%
Demolition | [8 empty] | 0 | 0 | 0 | 0%
Accute Group | USED | 141559 |  |  | 141559 | 0 |  |  | 141559 | 141559 | 0 | 0%
Downwell Demolition |  | 162750 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Maldon Demolition |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Diamond Drilling
Frog | USED | 51298 |  | nett | 51298 | 0
Duct Cleaning - inc in JS Wright | [8 empty] | 0 | 0 | 0 | 0%
Ductclean |  | 26640 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
JS Wright |  | 31826
[9 empty] | 0 | 0 | 0 | 0%
Electrical Installation | [8 empty] | 0 | 0 | 0 | 0%
Switch Electrical Services |  | 392528 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
JS Wright | USED | 370050 |  | 2.5 | 370050 | 9251.25 |  |  | 360798.75 | 360798.75 | 0 | 0%
Oakmead Electrical |  | 351289 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Chelmsford Electrical Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Wheeler |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Watkins |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Fencing | [8 empty] | 0 | 0 | 0 | 0%
DSM Fencing Ltd |  | 19214.95 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Hickman Bros. Landscapes |  | 20890.2 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
The Fencing Partnership |  | 21026.62 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Tonbridge |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Wyatt & Sons Fencing | USED | 17190.12 |  | Nett | 17190.12 | 0 |  |  | 17190.12 | 17190.12 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Fire Curtain
Fire Curtain | USED | 5287 |  | nett | 5287 | 0
Flooring | [8 empty] | 0 | 0 | 0 | 0%
AC Flooring |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Accent Commercial |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Accent Flooring |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Advance Flooring Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Easifloor Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Gordon Lomond | USED | 48003 |  | Nett | 48003 | 0 |  |  | 48003 | 48003 | 0 | 0%
Hillingdon Flooring Co |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Paramount Flooring |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Pennells Carpets |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Flue Inslallation - inc in JS Wright | [8 empty] | 0 | 0 | 0 | 0%
Chim Flue |  | 56955 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
JS Wright |  | 72106
[9 empty] | 0 | 0 | 0 | 0%
IPS | [8 empty] | 0 | 0 | 0 | 0%
Armitage Vanesta |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Bushboard |  | 5038.6 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Excalibur |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Maxwood |  | 4288.44 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Total Laminate Systems |  | 3110 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Amwell Systems Ltd | USED | 9611.8 |  | Nett | 9611.8 | 0 |  | SPECIFIED | 9611.8 | 9611.8 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
IRS | [8 empty] | 0 | 0 | 0 | 0%
SCCI Alphatrac | USED | 15363.71 |  | Nett | 15363.71 | 0 |  |  | 15363.71 | 15363.71 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
LPM Groundworker | [8 empty] | 0 | 0 | 0 | 0%
GPB Construction ltd |  | 229298 |  | Nett |  |  |  | plugged rates | 0 | 0 | 0 | 0%
Kenward Groundworks |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Tamdown Group ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Nugent Groudnworks |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Drivepoint Contractors Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Hamilton Construction Services Ltd |  | 291782 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
London Groundworks Ltd |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Modebest RC Frame & Groundworks |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Newpoint |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
HPS | USED | 233937 |  | Nett | 233937 | 0 |  |  | 233937 | 233937 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Landscaping | [8 empty] | 0 | 0 | 0 | 0%
Dolwin & Gray |  | 19519.15 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Hickman Brothers | USED | 19467 |  | Nett | 19467 | 0 |  |  | 19467 | 19467 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Lightning Protection | [8 empty] | 0 | 0 | 0 | 0%
Lightning Protection Testing Ltd | USED | 10730 |  | Nett | 10730 | 0 |  |  | 10730 | 10730 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Mechanical | [8 empty] | 0 | 0 | 0 | 0%
JS Wright | USED | 1878478 |  | 2.5 | 1878478 | 46961.95 |  |  | 1831516.05 | 1831516.05 | 0 | 0%
H&V Serviceplan |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
T4 Mechanical Services |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Woodford Heating |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Metalworker- Balustrade | [8 empty] | 0 | 0 | 0 | 0%
MRK |  | 35004 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
1st Choice |  | NQ | - | - |  |  |  |  | 0 | 0 | 0 | 0%
Delta |  | 38523 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Premier | USED | 34687 |  | 2.5 | 34687 | 867.175 |  |  | 33819.825 | 33819.825 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Painting | [8 empty] | 0 | 0 | 0 | 0%
Barry Stewart & Sons | [8 empty] | 0 | 0 | 0 | 0%
Armour Contracts Ltd |  | 63033.18 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Assured Services | [8 empty] | 0 | 0 | 0 | 0%
K&M |  | 58538.5 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
A&B Decorators | USED | 53905 |  | Nett | 53905 | 0 |  |  | 53905 | 53905 | 0 | 0%
Smith & O Sullivan | [8 empty] | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Plastering/ Drylining | [8 empty] | 0 | 0 | 0 | 0%
Accent Commercial | [8 empty] | 0 | 0 | 0 | 0%
Cadons Ltd | [8 empty] | 0 | 0 | 0 | 0%
Plastering Contracts (Stanmore) |  | 148861 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
SD Plastering | USED | 139139 |  | Nett | 139139 | 0 |  |  | 139139 | 139139 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Play Equipment | [8 empty] | 0 | 0 | 0 | 0%
Fenland leisure | [8 empty] | 0 | 0 | 0 | 0%
Handmade Places Ltd | [8 empty] | 0 | 0 | 0 | 0%
Kompan | USED | 49689 |  | Nett | 49689 | 0 |  |  | 49689 | 49689 | 0 | 0%
Lappset UK Ltd | [8 empty] | 0 | 0 | 0 | 0%
SMP | [8 empty] | 0 | 0 | 0 | 0%
Sovereign Play Equipment | [8 empty] | 0 | 0 | 0 | 0%
Timberline Ltd | [8 empty] | 0 | 0 | 0 | 0%
Wicksteed | [8 empty] | 0 | 0 | 0 | 0%
HPS |  | 73042.78 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Playtop Surfaces | [8 empty] | 0 | 0 | 0 | 0%
Playtop | USED | 20400 |  | Nett | 20400 | 0 |  |  | 20400 | 20400 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Roller Shutters | [8 empty] | 0 | 0 | 0 | 0%
Fortress | USED | 8537 |  | Nett | 8537 | 0 |  |  | 8537 | 8537 | 0 | 0%
Bolton Gate Company Ltd |  | 15284 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Charter Specialist Security |  | 12789 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Continental Shutters |  | 12354 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Coopers Fire Ltd |  | 18836 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Harlech Ind Doors Ltd |  | 12373 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Armashield |  | 22335 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Syston
[9 empty] | 0 | 0 | 0 | 0%
Steel Doors - inc in Harleys Package
Harlech |  | 5130 |  | nett
Prima Doors |  | 3951.29 |  | nett
Harley |  | 6088 |  | nett
Sports Floor - Beon Boflex | [8 empty] | 0 | 0 | 0 | 0%
Timbertype |  | 31409.22 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Pica Flooring | USED | 21657.18 |  | Nett | 21657.18 | 0 |  |  | 21657.18 | 21657.18 | 0 | 0%
21st Century Floors |  | 21776.66 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Westby |  | 22683.06 |  | 2.5 |  |  |  |  | 0 | 0 | 0 | 0%
HF Hutchison |  | 23082.7 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Structural Steel | [8 empty] | 0 | 0 | 0 | 0%
1st Choice | USED | 40168 |  | Nett | 40168 | 0 |  | £1400/tonne | 40168 | 40168 | 0 | 0%
AGP |  | 44751 |  | nett |  |  |  | £1942/tonne
[9 empty] | 0 | 0 | 0 | 0%
Suspended Ceilings
SD Plastering | USED | 21419 |  |  | 21419 | 0
Accent |  | 23928
Cadons |  | 21063
Stanmore |  | 24034
Tarmac | [8 empty] | 0 | 0 | 0 | 0%
Tarmac | USED | 23029.6 |  | 2.5 | 23029.6 | 575.74 |  |  | 22453.86 | 22453.86 | 0 | 0%
HPS |  | 29605.26 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
GPB |  | 36245 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
Hamilton |  | 41675 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Water Tank Overhaul and Duct Cleaning - inc in JS Wright | [8 empty] | 0 | 0 | 0 | 0%
Swiftclean |  | 76206 |  | Nett |  |  |  |  | 0 | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0 | 0%
Rydon Values
Lift Maintenace | USED | 30000 |  |  | 30000 | 0
Piling | USED | 10000 |  |  | 10000 | 0
Signage | USED | 12300 |  |  | 12300 | 0
Mastic | USED | 2290 |  |  | 2290 | 0
Glazing | USED | 1500 |  |  | 1500 | 0
Muck Away | USED | 15900 |  |  | 15900 | 0
Temporary/Facilitating Works | USED | 20250 |  |  | 20250 | 0
Garage Doors | USED | 9500 |  |  | 9500 | 0
Metal Railings | USED | 1750 |  |  | 1750 | 0
Street Lighting | USED | 3600 |  |  | 3600 | 0
BWIC | USED | 1800 |  |  | 1800 | 0
MG Asphalt | USED | 1050 |  |  | 1050 | 0
MG - General | USED | 7000 |  |  | 7000 | 0
Screed | USED | 13740 |  |  | 13740 | 0
[9 empty] | 0 | 0 | 0 | 0%
TOTAL |  |  |  |  | 6683809.34 | 154206.915 | 0 |  | #REF! | #REF! | #REF! | #REF!
[9 empty] | 6529602.425 |  | #REF!

## Quals
Rydon Construction |  |  | 2026-07-29 15:31
Tender Amplifications
It is our practice to append amplifications to every tender in order to clarify as fully as possible the basis of our submission. This avoids future doubt and highlights issues which need to be addressed in contract discussions.
Generally we comply with the employer's requirements but wish to clarify our tender as follows:
1 | This offer is subject to contract.
2 | If our tender is under consideration we would need to discuss the conditions of contract, wording of the bond and other ancillary documents.
3 | Our tender is exclusive of VAT.
4. | We confirm that we have made no allowance in our bid for Section 106 payments or commuted sums
5 | We would wish to see the land title documents before commenting on wayleaves, easements and rights of way.
Staged payments/milestone schedules
We have priced the scheme as drawn and assume it complies with the employer's spacial requirements.
Should we be successful we would wish drawings to be made available in CAD format and reports to be assigned to us with no charge.
For clarity we confirm no allowance has been made for the following:
Asbestos
Party wall surveyors, fees or works
Rights of Light surveyors, fees of works, insurance or compensation
Japanese Knotweed
Section 106 payments or commuted sums in respect of any adoption agreements
Planning fees
Ordnance removal
Costs or delays associated with archaeological interest
Contamination

## Summary Breakdown
GREN-02 | Nett | [9 empty] | 1.075 |  |  |  | 1.075 |  |  |  | 1.075 |  |  |  | 1.075 |  |  |  | 1.075 |  |  |  | 1.075 |  |  |  | 1.075 |  |  | 1.075 |  |  | 1.075 |  |  | 1.075 |  |  | 1.075
[11 empty] | B1 |  |  |  | B2 |  |  |  | B3 |  |  |  | B4 |  |  |  | B5 |  |  |  | B6 |  |  |  | B7 |  |  | B8 |  |  | B9 |  |  | B10 |  |  | B11
[5 empty] | Material | SC | BL | CJ | GW | Sums | 7 NR NEW UNITS |  |  |  | WORKS TO EXISTING FLATS |  |  |  | NURSERY & PLAY AREA |  |  |  | EMB OFFICES |  |  |  | BOXING CLUB |  |  |  | WORKS TO UNDERCROFT |  |  |  | M&E |  |  | #REF! |  |  | EXISTING GARAGES |  |  | #REF! |  |  | EXTERNAL WORKS |  |  | DRAINAGE
& COMMON AREAS
Bill 1 | Substructures | SUBSTRUCTURES | 19261.37 | 19261.37 | 0 | 19261.37 | 0 | 0 | 0 | 0 | [27 empty] | 19261.37
Bill 2 | Strip Out |  |  | 42369.89 | 0 | 42369.89 | 0 | 0 | 0 | 0 |  |  |  |  | 42369.89 | 42369.89 | 45547.6318 | 1.2
Bill 2 | Asbestos Removal |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bill 2 | Demolition | GENERAL WORKS TO EXTG | 130490.72 | 88120.83 | 0 | 88120.83 | 0 | 0 | 0 | 0
Bill 3 | Core Alterations - Ground Floor |  |  | 6443.26 | 0 | 6443.26 | 0 | 0 | 0 | 0 |  |  |  |  | 6443.26
Bill 3 | Core Alterations - Mezzanine Floor |  |  | 19767.52 | 0 | 19767.52 | 0 | 0 | 0 | 0 |  |  |  |  | 19767.52
Bill 3 | Core Alterations - Walkway Floor |  |  | 3825.17 | 0 | 3825.17 | 0 | 0 | 0 | 0 |  |  |  |  | 3825.17
Bill 3 | Core Alterations - Walkway +1 | CORE ALTERARTIONS | 63406.32 | 33370.37 | 0 | 33370.37 | 0 | 0 | 0 | 0 |  |  |  |  | 33370.37
Bill 4 | Roof **** |  |  | 1582.22 | 292.4 | 1000 | 0 | 289.82 | 0 | 0 | [5 empty] | 63406.32 | 68161.794 | 2.3 | [19 empty] | 1582.22
Bill 4 | Decorative Screen/Cladding to Roof *** |  |  | 763493 | 0 | 763493 | 0 | 0 | 0 | 0 | [27 empty] | 763493
Bill 4 | Entrance Canopy & Steel Pergola |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | 0
Bill 4 | Cladding |  |  | 915737 | 0 | 915737 | 0 | 0 | 0 | 0 | [27 empty] | 915737
Bill 4 | Curtain Walling |  |  | 110066 | 0 | 110066 | 0 | 0 | 0 | 0 | [27 empty] | 110066
Bill 4 | Windows |  |  | 1422976 | 0 | 1422976 | 0 | 0 | 0 | 0 | [27 empty] | 1422976
Bill 4 | External Doors *** |  |  | 6088 | 0 | 6088 | 0 | 0 | 0 | 0 | [27 empty] | 6088
Bill 4 | Roller Shutters | CLADDING & WINDOWS | 3228479.22 | 8537 | 0 | 8537 | 0 | 0 | 0 | 0 |  |  |  |  | 8537 | 8537 | 9177.275 | 2.21 | [20 empty] | 3219942.22 | 3461437.8865
Bill 5 | Composite Deck & Slab Infill - GF |  |  | 2273.27 | 0 | 2273.27 | 0 | 0 | 0 | 0 |  |  |  |  | 2273.27 |  |  | 2.2
Bill 5 | Composite Deck & Slab Infill - Mezzanine |  |  | 58261.18 | 0 | 58261.18 | 0 | 0 | 0 | 0 | 58261.18
Bill 5 | Composite Deck & Slab Infill - Walkway |  |  | 6944.58 | 0 | 6944.58 | 0 | 0 | 0 | 0 | 6944.58
Bill 5 | Composite Deck & Slab Infill - Walkway +1 |  |  | 19649.37 | 24.14 | 19528.1 | 97.13 | 0 | 0 | 0 | 19649.37
Bill 6 | Steelwork - Ground Floor |  |  | 3725.13 | 43.29 | 3326 | 271.44 | 84.4 | 0 | 0 |  | 84855.13 | 91219.2648 | 2.2 | 3725.13 | 5998.4 | 6448.28 | 2.2
Bill 6 | Steelwork - Mezzanine |  |  | 25470.14 | 0 | 25103 | 0 | 367.14 | 0 | 0 | 25470.14
Bill 6 | Steelwork - Walkway |  |  | 1267 | 0 | 1139 | 0 | 128 | 0 | 0 | 1267
Bill 6 | Steelwork - Walkway +1 | SUPERSTRUCTURE | 135903.67 | 18313 | 0 | 18313 | 0 | 0 | 0 | 0 | 18313 | 45050.14 | 48428.9005 | 2.4
Bill 10 | Party Walls - B1 |  |  | 10195.94 | 0 | 10195.94 | 0 | 0 | 0 | 0 | 10195.94
Bill 10 | Internals - Flats - B1 |  |  | 137791.19 | 45610.25 | 75690.54 | 778.38 | 15712.02 | 0 | 0 | 137791.19
Bill 10 | Decorations - New Flats | NEW FLATS | 158740.98 | 10753.85 | 0 | 10753.85 | 0 | 0 | 0 | 0 | 10753.85
Bill 20 | Works to Existing Flats - B2 |  |  | 262197.08 | 172275.14 | 1800 | 0 | 88121.94 | 0 | 0 |  | 158740.98 | 170646.5535 | 3.3 | 262197.08 | 262197.08 | 281861.861
Bill 20 | Common Areas/Lift Lobbies - B2 |  |  | 112068.17 | 19751.39 | 85564.27 | 607.43 | 6145.08 | 0 | 0 |  |  |  |  | 112068.17 | 112068.17 | 120473.2827
Bill 20 | Refuse Chute - B2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Bill 20 | Decorations - Works to Extg Flats - B2 |  |  | 14548 | 0 | 14548 | 0 | 0 | 0 | 0 |  |  |  |  | 14548
Bill 20 | Decoration- Commons Areas/Lift Lobbies B2 | EXISTING FLATS | 391048 | 2234.75 | 0 | 2234.75 | 0 | 0 | 0 | 0 |  |  |  |  | 2234.75 | 16782.75 | 18041.4562 | 3.1
Bill 30 | Party Walls - B3 |  |  | 4160.85 | 0 | 4160.85 | 0 | 0 | 0 | 0 | [8 empty] | 4160.85 | 4160.85
Bill 30 | Internals - B3 |  |  | 90449.01 | 30077.44 | 55862.43 | 0 | 4509.14 | 0 | 0 | [8 empty] | 90449.01 | 94609.86 | 101705.5995 | 2.18
Bill 30 | Decoration - Nursery etc B3 | NURSERY | 97218.96 | 2609.1 | 0 | 2609.1 | 0 | 0 | 0 | 0 | [8 empty] | 2609.1 | 2609.1 | 2804.7825 | 3.1
Bill 40 | Internals - B4 |  |  | 53511.68 | 11019.74 | 38324.83 | 0 | 4167.11 | 0 | 0 | [9 empty] | 97218.96 | 104510.382 |  | 53511.68 | 53511.68 | 57525.056 | 2.18
Bill 40 | Decorations - EMB Offices etc - B4 | OFFICES | 55835.03 | 2323.35 | 0 | 2323.35 | 0 | 0 | 0 | 0 | [12 empty] | 2323.35 | 2323.35 | 2497.6013 | 3.1
Bill 50 | Party Walls - B5 Boxing Club |  |  | 1477.89 | 437.2 | 0 | 1040.69 | 0 | 0 | 0 | [13 empty] | 55835.03 | 60022.6572 |  | 1477.89
Bill 50 | Internals - B5 Boxing Club |  |  | 56902.47 | 9251.68 | 42284.59 | 4186.18 | 1180.02 | 0 | 0 | [16 empty] | 56902.47 | 58380.36 | 62758.887 | 2.18
Bill 50 | Common Areas - B5 |  |  | 28835.23 | 1659.84 | 26343.39 | 0 | 832 | 0 | 0 | [16 empty] | 28835.23
Bill 50 | Decoration - Common Areas B5 |  |  | 2200 | 0 | 2200 | 0 | 0 | 0 | 0 | [16 empty] | 2200
Bill 50 | Decoration - Boxing Club B5 | BOXING CLUB | 90266.94 | 851.35 | 0 | 851.35 | 0 | 0 | 0 | 0 | [16 empty] | 851.35 | 31886.58 | 34278.0735 | 3.1
Bill 60 | Works to Undercroft - B6 | UNDERCROFT | 9725 | 9725 | 0 | 9725 | 0 | 0 | 0 | 0 | [17 empty] | 90266.94 | 97036.9605 |  | 9725
Bill 70 | Central Electrical Services - B7 |  |  | 396143.71 | 0 | 396143.71 | 0 | 0 | 0 | 0 | [21 empty] | 9725 | 10454.375 |  | 396143.71
Bill 70 | Central Mechanical Services - B7 | M&E | 2274621.71 | 1878478 | 0 | 1878478 | 0 | 0 | 0 | 0 | [24 empty] | 1878478
Bill 90 | Works to existing garages - B9 |  |  | 24215.65 | 0 | 24215.65 | 0 | 0 | 0 | 0 | [25 empty] | 2274621.71 | 2445218.3383 |  |  |  | 24215.65
Bill 90 | New Garage Wall - B9 | WORKS TO EXISTING GARGAES | 36074.37 | 11858.72 | 2956.56 | 1755 | 7147.16 | 0 | 0 | 0 | [30 empty] | 11858.72
Bill 110 | Site Preparation Works |  |  | 28767.66 | 0 | 28767.66 | 0 | 0 | 0 | 0 | [31 empty] | 36074.37 | 38779.9477 | 8.16 |  |  | 28767.66
Bill 110 | Demolition to Extg External Stepped Ramp |  |  | 11068.27 | 0 | 11068.27 | 0 | 0 | 0 | 0 | [36 empty] | 11068.27
Bill 110 | Adopted Road/Paths - Concrete Pavior |  |  | 185709.22 | 0 | 185709.22 | 0 | 0 | 0 | 0 | [36 empty] | 185709.22
Bill 110 | Play Area |  |  | 81361.24 | 0 | 81361.24 | 0 | 0 | 0 | 0 | [36 empty] | 81361.24
Bill 110 | Communal Planted Gardens |  |  | 29740.51 | 0 | 29740.51 | 0 | 0 | 0 | 0 | [36 empty] | 29740.51
Bill 110 | Screen Wall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [36 empty] | 0
Bill 110 | Fencing & Gates |  |  | 17591.77 | 0 | 17591.77 | 0 | 0 | 0 | 0 | [36 empty] | 17591.77
Bill 110 | Sundry Items | EXTERNAL WORKS | 361408.45 | 7169.78 | 0 | 7169.78 | 0 | 0 | 0 | 0 | [36 empty] | 7169.78
Bill 120 | Surface Water Runs | DRAINAGE | 31367.83 | 31367.83 | 0 | 31367.83 | 0 | 0 | 0 | 0 | [36 empty] | 31367.83
Bill 130 | External Lighting | SERVICES | 5025.93 | 5025.93 | 0 | 5025.93 | 0 | 0 | 0 | 0 | [36 empty] | 5025.93
Bill 140 | Facilitating Works **** | FACILITATING WORKS | 24025.93 | 24025.93 | 0 | 24025.93 | 0 | 0 | 0 | 0 |  |  |  |  | 24025.93 | [32 empty] | 397802.21 | 427637.3758
Bill 400 | Provisional Sums | PROV SUMS | 212550 | 212550 | 0 | 0 | 0 | 0 | 0 | 212550
Bill 500 | Cost for Alternative Design |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7325450.43 | 7325450.43 | 293399.07 | 6683836.28 | 14128.41 | 121536.67 | 0 | 212550 | 288646.25 |  |  |  | 535385.54 |  |  |  | 97218.96 |  |  |  | 55835.03 |  |  |  | 90266.94 |  |  |  | 9725 |  |  |  | 2274621.71 |  |  | 3239203.59 |  |  | 36074.37 |  |  |  | 0 | 0 | 397802.21
7325450.43
[12 empty] | 288646.25 | 310294.7188 |  |  | 511359.61 | 549711.5807 |  |  | 198598.77 | 209020.764 |  |  | 111670.06 | 120045.3145 |  |  | 180533.88 | 194073.921 |  |  | 9725 | 10454.375 | 3.3 |  | 2274621.71 | 2445218.3383 |  | 3219942.22 | 3461437.8865 |  | 36074.37 | 38779.9477 |  |  |  |  | 397802.21 | 427637.3758
84855.13
91219.2648
45050.14
[11 empty] | 48428.9005 |  |  |  | 180458.7 | [15 empty] | 7422.25
[15 empty] | 193993.1025 |  |  | 3.7 | [12 empty] | 7978.9187 | 3.3 | [8 empty] | 24215.65 | [5 empty] | 28767.66
[11 empty] | 158740.98 |  |  |  | 15389.28 | [15 empty] | 2302.75 | [9 empty] | 26031.8237 |  |  | 8.16 |  |  | 30925.2345 |  |  | 8.1
[15 empty] | 16543.476 |  |  | 3.4 | [12 empty] | 2475.4563 | [9 empty] | 11858.72 | [5 empty] | 185709.22
[11 empty] | 170646.5535 |  |  |  | 17463.18 | [25 empty] | 12748.124 |  |  | 8.16 |  |  | 199637.4115 |  |  | 8.4
[15 empty] | 18772.9185 |  |  | 3.5 | [12 empty] | 9725 | [15 empty] | 81361.24
[15 empty] | 17066.43 | [31 empty] | 87463.333 |  |  | 8.5
[15 empty] | 18346.4123 |  |  | 2.2 | [28 empty] | 29740.51
[47 empty] | 31971.0482 |  |  | 8.6
[11 empty] | 288646.25 |  |  |  | 230377.59 | [31 empty] | 17591.77
[11 empty] | 310294.7188 | [35 empty] | 18911.1528 |  |  | 8.7
[15 empty] | 16303.9 | [31 empty] | 7169.78
[11 empty] | 310294.7188 |  |  |  | 17526.6925 |  |  | 2.18 | [28 empty] | 7707.5135 |  |  | 8.16
[15 empty] | 11743.44 | [31 empty] | 31367.83
[15 empty] | 12624.198 |  |  | 2.17 | [28 empty] | 33720.4172 |  |  | 8.14
[15 empty] | 6229.14 | 16782.75 | [30 empty] | 5025.93
[16 empty] | 23011.89 | 24737.7817 | 3.1 | [28 empty] | 5402.8747 |  |  | 8.15
12931.77
[15 empty] | 13901.6527 |  |  | 3.2
1110.98
[15 empty] | 1194.3035 |  |  | 3.3
1545
[15 empty] | 1660.875 |  |  | 3.6
30000
[15 empty] | 32250 |  |  | 2.22
79864.23
[15 empty] | 42369.89 | 42369.89 | 45547.6318 | 7.1
8.2
[15 empty] | 10592.4725 | 10592.4725 | 11386.9079 | 7.1 | B11
[15 empty] | 31777.4175 | 31777.4175 | 34160.7238 | 8.2 | B11
45547.6318

## Sheet1
GREN-01 Nett
| Description | Qty | Unit | Rate | £ p | 1.073
Bill 10 B1 - 7 NR UNITS SOCIAL HOUSE - Internals - Flats - B1
SUBCONTRACTORS
Electrical Installation all in accordance with the Employers Requirements
1A | 1B2P Flat | 1 | nr | 0 | 0 | 0
Electrical Installation all in accordance with the Employers Requirements
2A | 2B3P Flat | 2 | nr | 0 | 0 | 0
0
3A | 4B6P Flat | 3 | nr | 0 | 0 | 0
0
4A | 3B4P Flat WC | 1 | nr | 0 | 0 | 0
0
| Page Total 10/2/11 |  |  |  | 0 | 0
0
| Bill 20 B2 - WORKS TO EXTG FLATS & COMMON AREAS - Works to Existing Flats - B2 |  |  |  |  | 0
0
| SUBCONTRACTORS |  |  |  |  | 0
0
| Electrical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
1A | Existing 1B2P Flat | 40 | nr | 0 | 0 | 0
0
| Electrical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
2A | Existing 2B4P Flat | 80 | nr | 0 | 0 | 0
0
| Page Total 20/1/5 |  |  |  | 0 | 0
0
| Bill 20 B2 - WORKS TO EXTG FLATS & COMMON AREAS - Common Areas/Lift Lobbies - B2 |  |  |  |  | 0
0
| SUBCONTRACTORS |  |  |  |  | 0
0
| Electrical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
1A | B2 - Common Areas, Lift Lobbies & Refuse Chute | 1 | item | 0 | 0 | 0
0
| Page Total 20/2/8 |  |  |  | 0 | 0
0
| Bill 30 B3 - NURSERY, PLAY AREA, MEETING ROOM & LOBBY - Internals - B3 |  |  |  |  | 0
0
14A | Hand dryer, Xlerator ref XLW 500W or similar | 3 | nr | 150 | 450 | 160.95
0
| Page Total 30/2/9 |  |  |  | 450 | 0
0
| SUBCONTRACTORS |  |  |  |  | 0
0
| Electrical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
1A | B3 - Nursery, Play Area, Meeting Room & Lobbies | 1 | item | 0 | 0 | 0
0
| Page Total 30/2/11 |  |  |  | 0 | 0
0
| Bill 40 B4 - EMB OFFICES COMM MEETING ROOM ETC - Internals - B4 |  |  |  |  | 0
0
14A | Hand dryer, Xlerator ref XLW 500W or similar | 2 | nr | 150 | 300 | 160.95
0
| Page Total 40/1/9 |  |  |  | 300 | 0
0
| SUBCONTRACTORS |  |  |  |  | 0
0
| Electrical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
1A | B4 - EMB offices, Community Meeting Room, Lobbies, Store Room & Staircase A1 | 1 | item | 0 | 0 | 0
0
| Page Total 40/1/11 |  |  |  | 0 | 0
0
| Bill 50 B5 - BOXING CLUB INC TOILET & STAIR - Internals - B5 Boxing Club |  |  |  |  | 0
0
14A | Hand dryer, Xlerator ref XLW 500W or similar | 2 | nr | 150 | 300 | 160.95
0
| Page Total 50/2/9 |  |  |  | 300 | 0
0
| SUBCONTRACTORS |  |  |  |  | 0
0
| Electrical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
1A | B5 - Boxing Club | 1 | item | 0 | 0 | 0
0
| Page Total 50/2/11 |  |  |  | 0 | 0
0
| Bill 50 B5 - BOXING CLUB INC TOILET & STAIR - Common Areas - B5 |  |  |  |  | 0
0
1A | B5 - Common Areas (Staircase) | 1 | item | 0 | 0 | 0
0
| Page Total 50/3/7 |  |  |  | 0 | 0
Bill 70 B7 CENTRAL MECHCHANICAL & ELECTRICAL SERVICES - Central Electrical Services - B7
1A | CAP OFF EXISTING SERVICES | 1 | item | 3286 | 3286 | 3525.878
2A | REMOVAL OF REDUNDANT, STRIP OUT OF SERVICES | 1 | item | 6572 | 6572 | 7051.756
3A | MODIFICATION WORK/RELOCATION OF EXISTING ELECTRICAL SERVICES | 1 | item | 16429 | 16429 | 17628.317
4A | TEMPORARY WORKS PACKAGES FOR THE SERVICES | 1 | item | 9716 | 9716 | 10425.268
5A | MAIN & SUB MAIN DISTRIBUTION | 1 | item | 16025 | 16025 | 17194.825 | 4782 |  | 1735 | 5382 | 4126 | 16025
[7 empty] | 5131.086 |  | 1861.655 | 5774.886 | 4427.198 | 17194.825
6A | CABLE TRAY AND TRUNKING INSTALLATION | 1 | item | 9831 | 9831 | 10548.663
7A | GENERAL LIGHTING | 1 | item | 119432 | 119432 | 128150.536 | 10106 | 28424 | 61328 |  |  |  | 19574 | 119432
[7 empty] | 10843.738 | 30498.952 | 65804.944 |  |  | 0 | 21002.902 | 128150.536
8A | EMERGENCY LIGHTING | 1 | item | 0 | 0 | 0
9A | RELOCATION OF EXISTING LIGHTING | 1 | item | 0 | 0 | 0
10A | GENERAL PURPOSE POWER & ANCILLARY POWER INSTALLATIONS | 1 | item | 51105 | 51105 | 54835.665 | 10289 | 24574 | 12170 |  | 4072 | 51105
[7 empty] | 11040.097 | 26367.902 | 13058.41 |  | 4369.256 | 54835.665
11A | CONTROLS & ELECTRICAL WIRINGS | 1 | item | 12128 | 12128 | 13013.344 | 1404 | 10724 |  |  |  | 12128
[7 empty] | 1506.492 | 11506.852
12A | FIRE DECTECTION & ALARM SYSTEMS | 1 | item | 31961 | 31961 | 34294.153 | 2065 |  | 3490 | 4905 | 21501 | 31961
[7 empty] | 2215.745 |  | 3744.77 | 5263.065 | 23070.573 | 34294.153
13A | ACCESS CONTROL INSTALLATION & ENTRY PHONE | 1 | item | 35832 | 35832 | 38447.736
14A | FACILITIES FOR THE DISABLED | 1 | item | 0 | 0 | 0
15A | CCTV INSTALLATION | 1 | item | 7665 | 7665 | 8224.545
16A | EXTENSION OF THE COMMUNAL TV SYSTEM | 1 | item | 3773 | 3773 | 4048.429
17A | TV & COMMUNAL SATELLITE | 1 | item | 7810 | 7810 | 8380.13
18A | CONTAINMENT FOR TELEPHONE & DATA WIRING | 1 | item | 1630 | 1630 | 1748.99
19A | VOICE & DATA INSTALLATION | 1 | item | 10000 | 10000 | 10730
20A | DISABLED TOILET ALARM SYSTEMS | 1 | item | 2096 | 2096 | 2249.008
21A | EARTHING & BONDING INSTALLATION | 1 | item | 1656 | 1656 | 1776.888
22A | LIGHTNING PROTECTION SYSTEM | 1 | item | 918 | 918 | 985.014
23A | ICT / BUILDING MANAGEMENT SYSTEM | 1 | item | 0 | 0 | 0
24A | DESIGN OF ELECTRICAL ENGINEERING SERVICES | 1 | item | 8912 | 8912 | 9562.576
25A | PROVISION OF WORKING DRAWINGS, RECORD DRAWINGS & MAINTENANCE MANUAL | 1 | item | 6289 | 6289 | 6748.097
26A | ANY OTHER WORKS NOT INCLUDED ABOVE - CONTRACTOR TO DEFINE | 1 | item | 23077.71 | 23077.71 | 24762.3828
| Page Total 70/1/1 |  |  |  | 370050 | 414332.2008
Bill 130 B11 - SERVICES - External Lighting
Decorative post top latern; Thorn as V(21)500 light fitting schedule
4A | As schedule ref L6 - Avenue F ref 96260029 | 12 | nr | 300 | 3600
| Page Total 130/1/1 |  |  |  | 3600
0
26A | ANY OTHER WORKS NOT INCLUDED ABOVE - CONTRACTOR TO DEFINE | 1 | item | 23077.71 | 23077.71 | 24762.3828
| Preliminaroe |  |  | 6984
| IRS Sytem |  |  | 15363.71
| Works to existing Lighning Protection |  |  | 730
23077.71

## Sheet2
GREN-01 Nett
| Description | Qty | Unit | Rate | £ p | 1.072
Bill 10 B1 - 7 NR UNITS SOCIAL HOUSE - Internals - Flats - B1
Mechanical Installation all in accordance with the Employers Requirements
5A | 1B2P Flat | 1 | nr | 0 | 0 | 0
0
6A | 2B4P Flat | 2 | nr | 0 | 0 | 0
0
7A | 4B6P Flat | 3 | nr | 0 | 0 | 0
0
8A | 3B4P Flat WC | 1 | nr | 0 | 0 | 0
0
| Page Total 10/2/11 |  |  |  | 0 | 0
0
| Bill 20 B2 - WORKS TO EXTG FLATS & COMMON AREAS - Works to Existing Flats - B2 |  |  |  |  | 0
0
3A | Existing 1B2P Flat | 40 | nr | 0 | 0 | 0
0
4A | Existing 2B4P Flat | 80 | nr | 0 | 0 | 0
0
| Page Total 20/1/5 |  |  |  | 0 | 0
0
| Bill 20 B2 - WORKS TO EXTG FLATS & COMMON AREAS - Common Areas/Lift Lobbies - B2 |  |  |  |  | 0
0
| Thermally insulated Metal Louvres: Renson Fabrications as spec L10/653 |  |  |  |  | 0
0
| Glazed-in louvre panel ref 414THF to AOV shaft (internal) as drawing 1279 (06)101 |  |  |  |  | 0
0
6A | 1000 x 1600mm | 2 | nr | 0 | 0 | 0
0
| Pendock Profiles |  |  |  |  | 0
0
7A | 500 x 300mm Type MXD | 9 | m | 0 | 0 | 0
0
8A | External Corner detail Type MXD | 9 | m | 0 | 0 | 0
0
| Page Total 20/2/6 |  |  |  | 0 | 0
0
| Mechanical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
2A | B2 - Common Areas, Lift Lobbies & Refuse Chute | 1 | item | 0 | 0 | 0
0
| Page Total 20/2/8 |  |  |  | 0 | 0
0
| Bill 30 B3 - NURSERY, PLAY AREA, MEETING ROOM & LOBBY - Internals - B3 |  |  |  |  | 0
0
| High Level Louvre vent to AOV shaft (internal) (internal door schedule ref D1-34) |  |  |  |  | 0
0
6A | say 800 x 1000mm | 1 | nr | 0 | 0 | 0
0
| Page Total 30/2/7 |  |  |  | 0 | 0
0
| Mechanical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
5A | B3 - Nursery, Play Area, Meeting Room & Lobbies | 1 | item | 0 | 0 | 0
0
| Page Total 30/2/11 |  |  |  | 0 | 0
0
| Bill 40 B4 - EMB OFFICES COMM MEETING ROOM ETC - Internals - B4 |  |  |  |  | 0
0
| AOV for hot smoke release; Wicona UK as spec L10/691 |  |  |  |  | 0
0
| High Level Louvre vent to AOV shaft ref Wicline 65 evo; (internal door ref D3-13) |  |  |  |  | 0
0
6A | 2000 x 1000mm | 1 | nr | 55560 | 55560 | 59560.32
0
| Page Total 40/1/7 |  |  |  | 55560 | 0
0
| Mechanical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
5A | B4 - EMB offices, Community Meeting Room, Lobbies, Store Room & Staircase A1 | 1 | item | 0 | 0 | 0
0
| Page Total 40/1/11 |  |  |  | 0 | 0
0
| Bill 50 B5 - BOXING CLUB INC TOILET & STAIR - Internals - B5 Boxing Club |  |  |  |  | 0
0
| Sports Shower Panel; Delabie UK as spec N13/375B |  |  |  |  | 0
0
17A | Shower panel ref 714700GR and 825216 or similar including spray grid and soap dish ref 710500 | 2 | nr | 0 | 0 | 0
0
| Drinking Fountain; Franke Sissons as spec N13/379A |  |  |  |  | 0
0
18A | Fountain and bottle filler ref ANMX306 or similar | 1 | nr | 0 | 0 | 0
0
| Linear Drainage; ACO as spec N13/505 |  |  |  |  | 0
0
21A | Aco Modular 125 Intercept Grating (Locked) 125mm wide x 50mm deep x 500mm lengths | 3 | nr | 0 | 0 | 0
0
| Point Drainage Floor Gully; On the Level as spec N13/510 |  |  |  |  | 0
0
22A | Ref TSG2SS 50mm outlet x 130mm height | 2 | nr | 0 | 0 | 0
0
| Page Total 50/2/9 |  |  |  | 0 | 0
0
| Mechanical Installation all in accordance with the Employers Requirements |  |  |  |  | 0
0
2A | B5 - Boxing Club | 1 | item | 0 | 0 | 0
0
| Page Total 50/2/11 |  |  |  | 0 | 0
0
| Bill 50 B5 - BOXING CLUB INC TOILET & STAIR - Common Areas - B5 |  |  |  |  | 0
0
2A | B5 - Common Areas (Staircase) | 1 | item | 0 | 0 | 0
0
| Page Total 50/3/7 |  |  |  | 0 | 0
0
Bill 70 B7 CENTRAL MECHCHANICAL & ELECTRICAL SERVICES - Central Mechanical Services - B7
CENTRAL MECHANICAL SERVICES
1A | CAP OFF EXSITING SERVICES | 1 | item | 2283 | 2283 | 2447.376
2A | REMOVAL OF REDUNDANT, STRIP OUT OF EXISTING SERVICES | 1 | item | 16797 | 16797 | 18006.384
3A | MODIFICATION WORKS / RELOCATION OF EXISTING MECHANCIAL SERVICES | 1 | item | 3617 | 3617 | 3877.424
4A | DRY RISER | 1 | item | 13776 | 13776 | 14767.872
5A | ISOLATION ARRANGEMENT FOR HEATING PRIMARIES : 2 BRANHCES SERVING 3 FLATS EACH | 1 | item | 0 | 0
6A | TEMPORARY WORKS PACKAGES FOR THE SERVICES | 1 | item | 2689 | 2689 | 2882.608
7A | HEATING PLANT (INC FLUES, PRESSSURISATION ETC) | 1 | item | 358455 | 358455 | 384263.76 | 13711 | 235049 | 3088 | 4013 | 3088 | 99506 | 358455
[7 empty] | 14698.192 | 251972.528 | 3310.336 | 4301.936 | 3310.336 | 106670.432 | 384263.76
8A | HOT WATER INSTALLATION | 1 | item | 22342 | 22342 | 23950.624 | 4497 | 15552 | 1126 | 530 | 637 |  | 22342
[7 empty] | 4820.784 | 16671.744 | 1207.072 | 568.16 | 682.864 |  | 23950.624
9A | HEATING INSTALLATION | 1 | item | 580810 | 580810 | 622628.32 | 30180 | 447844 | 9581 | 10645 | 10276 | 72284 | 580810
[7 empty] | 32352.96 | 480088.768 | 10270.832 | 11411.44 | 11015.872 | 77488.448 | 622628.32
10A | MAIN CONTROLS INSTALLATION FOR LOW TEMPERATURE HOT WATER HEATING WITH STAND ALONE CONTROLS | 1 | item | 86806 | 86806 | 93056.032
11A | ONE LARGE RADIATOR IN LIVING ROOM, NONE IN KITCHEN AND ASSOC RE-DECORATION WORKS | 1 | item | 0 | 0
12A | REMOTE WIRELESS OPERATED METERING (FOR HEAT METERING) | 1 | item | 0 | 0
13A | NATURAL GAS INSTALLATIONS | 1 | item | 10953 | 10953 | 11741.616
14A | NEW BOILER PLANT WITH STANDARD SUB METER FOR GAS | 1 | item | 43707 | 43707 | 46853.904
15A | MAINS COLD WATER INSTALLATION | 1 | item | 148910 | 148910 | 159631.52 | 8394 | 85261 | 1774 | 1148 | 1334 | 50999 | 148910
[7 empty] | 8998.368 | 91399.792 | 1901.728 | 1230.656 | 1430.048 | 54670.928 | 159631.52
16A | ISOLATION TO EXISTING WATER TANKS | 1 | item | 1487 | 1487 | 1594.064
17A | STERILIZATION OF WATER SERVICES | 1 | item | 4506 | 4506 | 4830.432
18A | MECHANICAL VENTILATION SYSTEMS | 1 | item | 121847 | 121847 | 130619.984 | 7431 | 87919 | 1500 | 2310 | 1243 | 21444 | 121847
[7 empty] | 7966.032 | 94249.168 | 1608 | 2476.32 | 1332.496 | 22987.968 | 130619.984
19A | MECHANICAL / EXTRACT / VENTILATION SYSTEMS IN BASEMENT | 1 | item | 17515 | 17515 | 18776.08
20A | MECHANICAL SERVICES WIRING REQUIREMNT INSTALLATION | 1 | item | 0 | 0
21A | SMOKE EXTRACT SYSTEM | 1 | item | 78988 | 78988 | 84675.136
22A | ALTERATION WORKS TO MAIN FOUL DRAINAGE | 1 | item | 13705 | 13705 | 14691.76
23A | SANITARY PLUMBING / ABOVE GROUND DRAINAGE | 1 | item | 937 | 937 | 1004.464
24A | DESIGN OF MECHANICAL ENGINEERING SERVICES | 1 | item | 57938 | 57938 | 62109.536
25A | PROVISION OF WORKING DRAWINGS, RECORD DRAWINGS & MAINTENANCE MANUAL | 1 | item | 0 | 0
26A | TEMPORARY SERVICES | 1 | item | 0 | 0
27A | BWIC WITH SERVICES INCLUDING FORMING HOLES ETC | 1 | item | 0 | 0
28A | TESTING & COMMISSIONING OF SERVICES | 1 | item | 77557 | 77557 | 83141.104
29A | ANY OTHER WORKS NOT INCLUDED ABOVE - CONTRACTOR TO DEFINE | 1 | item | 296448 | 212853 | 317792.256
| Page Total 70/2/1 |  |  |  | 1878478 | 2103342.256
29A | ANY OTHER WORKS NOT INCLUDED ABOVE - CONTRACTOR TO DEFINE | 1 | item | 296448 | 212853 | 317792.256
| Preliminaries |  |  | 212853
| New fire protection valves |  |  | 26640
| Boiler flue installation |  |  | 56955
296448

## Sheet3
2014-01-30 | Grenfell Tower
1.075
| COST SUMMARY | Harley | 3D Aluminium Plas Ltd | Glassolutions | Advanced Glass | Fill Metallbau | Hasen Facades | B8
|  | Metal Technology | Wicona 75 | Wicona 75 | Wicona 75 | Wicona 75 | Wicona 75
|  | System 17 | System | System | System | System | System |  |  |  | 0.97
Item | Description
| Removal of existing windows and glazing | 64046 | Included | 64046 | 64046 | Included | Included | 64046 |  | 7.4 | 62124.62 | 66783.9665
0
| SFS Walling (Ground Floor to Level 3 ) | 30207 | 30207 | 30207 | 30207 | Included | Included | 30207 |  | 2.12 | 29300.79 | 31498.3492
[8 empty] | 0 |  |  | 0
| Curtain Walling (Ground Floor Level) | 110066 | Included | 39364.27 | 46659.72 | Included | Included | 46659.72 |  | 2.12 | 106764.02 | 114771.3215
[8 empty] | 0 |  |  | 0
| AOV actuators for natural ventilation | 4557 | 4557 | 4557 | 4557 | Included | Included | 4557 |  | 2.15 | 4420.29 | 4751.8117
[8 empty] | 0 |  |  | 0
| Windows (Mezzanine level and above) | 1422976 | 1192377 | 1121418.45 | 1254113.36 | 3253597 | 1815530 | 1254113.36 |  | 2.15 | 1380286.72 | 1483808.224
[8 empty] | 0 |  |  | 0
| Extra Over : Louvres to opening vents |  |  | 159158 | 7701.67 | Included | Included | 7701.67 |  | 2.15 | 0
0
| South Elevation | [6 empty] | 0
| Small |  | 51852 |  |  |  |  | 0
| Large |  | 1509 |  |  |  |  | 0
0
| North Elevation | [6 empty] | 0
| Small |  | 54832 |  |  |  |  | 0
| Large |  | 2012 |  |  |  |  | 0
0
| West Elevation | [6 empty] | 0
| Small |  | 61686 |  |  |  |  | 0
| Large |  | 3521 |  |  |  |  | 0
0
| East Elevation | [6 empty] | 0
| Small |  | 66752 |  |  |  |  | 0
| Large |  | 1509 |  |  |  |  | 0
0
| Perimeter Trims |  |  | 39041.33 | Included | Included | Included | Included
0
| Preliminaries | Included | Included | 147813.33 | Included | Included | Included | Included
0
0
0
0
0
| AOV actuators for smoke ventilation | 2527 | 2527 | 2527 | 2527 | Included | 2527 | 2527 |  | 2.15 | 2451.19 | 2635.0293
[8 empty] | 0 |  |  | 0
| GRC Column Cladding (Ground to Walkway Level | 77878 | 77878 | 77878 | 77878 | Included | 77878 | 77878 |  | 2.12 | 75541.66 | 81207.2845
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Zinc Column Cladding and Crown (Walkway Level to top of Crown | 551178 | 551178 | 551178 | 551178 | Included | 551178 | 551178 |  | 2.11 | 534642.66 | 574740.8595
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Zinc Rainscreen Cladding to Spandrel Panels ( Level 4 to Plant Level) | 707625 | 707625 | 707625 | 707625 | Included | 707625 | 707625 |  | 2.11 | 686396.25 | 737875.9688
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Alumimium Rainscreen Cladding Generally (Ground Floor to Level 3) | 109921 | 109921 | 109921 | 109921 | Included | 109921 | 109921 |  | 2.12 | 106623.37 | 114620.1227
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Cladding to Main Entrance Canopy | 11840 | 11840 | 11840 | 11840 | Included | 11840 | 11840 |  | 2.7 | 11484.8 | 12346.16
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Cladding to Nursery and Boxing Club Canopies | 8473 | 8473 | 8473 | 8473 | Included | 8473 | 8473 |  | 2.12 | 8218.81 | 8835.2208
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Steel Doors | 6088 | 6088 | 6088 | 6088 | Included | 6088 | 6088 |  | 2.12 | 5905.36 | 6348.262
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0
| Design, drawings, survey and schedules for procurement | 110978 | 110978 | 110978 | 110978 | Included | 110978 | 110978 |  | 2.12 | 107648.66 | 115722.3095
0
0
|  | 3218360 | 3057322 | 3192113.38 | 2993792.75 | 3253597 | 3402038 | 2993792.75
0
0
| Additional Costs | [6 empty] | 0
0
| Internal Reveals to Windows : Timber Cladding | 454905 | 454905 | 454905 | 454905 | 454905 | 454905 | 454905 |  | 2.16 | 441257.85 | 474352.1887
0
0
| Curtain Wall and Windows | [6 empty] | 0
0
| Wiconas Wictec 50 curtain walling and Woicline 65 evo windows | 114866 | included | included | included | included | included | included
0
0
0
|  | 3788131 | 3512227 | 3647018.38 | 3448697.75 | 3708502 | 3856943 | 3448697.75
0
| Additional costs | [6 empty] | 0
| Deduct Wiconas Wictec 50 curtain walling from Harley Quotation | 114866 | [5 empty] | 0
0
0
|  | 3673265 | 3512227 | 3647018.38 | 3448697.75 | 3708502 | 3856943 | 3448697.75
0
Cost for Alternative Design Solutions
Cladding:
New Aluminium cladding including necessary support, insulation, etc.
to façade of Tower
Harley
Alternatives
a) | Reynobond rainscreen cladding 1965m2 @ £120/m2 | 235800
| CGL Wallplank Rainscreen Panels 462m2@ £32/m2 | 14784
250584
b) | Alucobond rainscreen cladding 1965m2@ £120/m2 | 235800
| CGL Wallplank Rainscreen Panels 462m2@ £32/m2 | 14784
250584
| Harley Alternative Design Solutions Comparrison | 3422681 | 3512227 | 3647018.38 | 3448697.75 | 3708502 | 3856943
| Cladding to Main Entrance Canopy | 11840 | 11840 | 11840 | 11840 | Included | 11840 | 11840 | 11840 | 2.7 |  | 11484.8
[9 empty] | 12728 |  | 12728 | 12346.16 |  | 12346.16
| Zinc Column Cladding and Crown (Walkway Level to top of Crown | 551178 | 551178 | 551178 | 551178 | Included | 551178 | 551178 |  | 2.11 |  | 534642.66
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0
| Zinc Rainscreen Cladding to Spandrel Panels ( Level 4 to Plant Level) | 707625 | 707625 | 707625 | 707625 | Included | 707625 | 707625 | 1258803 | 2.11 |  | 686396.25 | 1221038.91
[9 empty] | 1353213.225 |  | 1353213.225 | 0 | 1312616.8283 | 1312616.8283
0
0
| SFS Walling (Ground Floor to Level 3 ) | 30207 | 30207 | 30207 | 30207 | Included | Included | 30207 |  | 2.12 |  | 29300.79
[8 empty] | 0 |  |  |  | 0
| Curtain Walling (Ground Floor Level) | 110066 | Included | 39364.27 | 46659.72 | Included | Included | 46659.72 |  | 2.12 |  | 106764.02
0
| GRC Column Cladding (Ground to Walkway Level | 77878 | 77878 | 77878 | 77878 | Included | 77878 | 77878 |  | 2.12 |  | 75541.66
0
| Alumimium Rainscreen Cladding Generally (Ground Floor to Level 3) | 109921 | 109921 | 109921 | 109921 | Included | 109921 | 109921 |  | 2.12 |  | 106623.37
0
| Cladding to Nursery and Boxing Club Canopies | 8473 | 8473 | 8473 | 8473 | Included | 8473 | 8473 |  | 2.12 |  | 8218.81
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0
| Steel Doors | 6088 | 6088 | 6088 | 6088 | Included | 6088 | 6088 |  | 2.12 |  | 5905.36
|  |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0
| Design, drawings, survey and schedules for procurement | 110978 | 110978 | 110978 | 110978 | Included | 110978 | 110978 | 390204.72 | 2.12 |  | 107648.66 | 440002.67
[9 empty] | 419470.074 |  | 419470.074 | 0 | 473002.8702 | 473002.8702
| AOV actuators for smoke ventilation | 2527 | 2527 | 2527 | 2527 | Included | 2527 | 2527 |  | 2.15 |  | 2451.19
0
| AOV actuators for natural ventilation | 4557 | 4557 | 4557 | 4557 | Included | Included | 4557 |  | 2.15 |  | 4420.29
[8 empty] | 0 |  |  |  | 0
| Windows (Mezzanine level and above) | 1422976 | 1192377 | 1121418.45 | 1254113.36 | 3253597 | 1815530 | 1254113.36 |  | 2.15 |  | 1380286.72
[8 empty] | 0 |  |  |  | 0
| Extra Over : Louvres to opening vents |  |  | 159158 | 7701.67 | Included | Included | 7701.67 | 1268899.03 | 2.15 |  | 0 | 1387158.2
[9 empty] | 1364066.4572 |  | 1364066.4572 | 0 | 1491195.065 | 1491195.065
0
0
| Internal Reveals to Windows : Timber Cladding | 454905 | 454905 | 454905 | 454905 | 454905 | 454905 | 454905 | 454905 | 2.16 |  | 441257.85 | 441257.85
[9 empty] | 489022.875 |  | 489022.875 | 0 | 474352.1887 | 474352.1887
0
| Removal of existing windows and glazing | 64046 | Included | 64046 | 64046 | Included | Included | 64046 | 64046 | 7.4 |  | 62124.62 | 62124.62
[9 empty] | 68849.45 |  | 68849.45 |  | 66783.9665 | 66783.9665
[8 empty] | 3448697.75 |  |  | 3707350.0812 |  |  | 3830297.0787